## Instructions
WCE Estimator - full-SDLC input template
This template lists the work areas of a complete delivery lifecycle so nothing
is forgotten. Method: Work-Class Estimation with the Khan Ceiling (Viquar Khan).
How to use:
1. The tabs (Discovery & Planning, Cloud & Infrastructure, Backend & Data,
Frontend, Quality & Testing, Release & Ops) are a checklist of process
areas. Keep the rows that apply, delete those that do not, add your own.
2. The grey rows are EXAMPLES with placeholder baselines - replace the
'Baseline (PM)' numbers with your own estimate per work item.
3. Required columns : 'Work Item' and 'Baseline (PM)' (rename the effort
column to Effort / Estimate / Days / Hours / Points if you prefer).
4. Optional columns:
Work Class - auto-classifies the AI multiplier if left as given
(Requirements, Architecture, Data modeling, UX design,
Cloud infra, Observability, REST API, Database,
Integration, Security, Concurrency, React UI,
Simple page, Test planning, Test automation,
Manual testing, Performance testing, Review,
Deployment, Documentation, Support, Agile ceremonies,
Compliance, Coordination, Data migration)
AI Difficulty - Low / Medium / High (optional override; AI-resistance,
NOT business size). Ignored for essential classes.
Essential - Yes/No (work AI cannot remove: requirements, design,
architecture, ceremonies, compliance). Sets the ceiling.
a_low/a_mode/a_high - explicit multiplier band, overrides everything.
5. Optional 'Config' tab sets Team Size, Unit, Claim, Project.
AI effort multiplier a: a < 1 faster, a = 1 no change, a > 1 slower.
Run (web) : python app.py then open http://127.0.0.1:5000
Run (CLI) : python estimate.py input\<this file>.xlsx -o reports --compare --open

## Discovery & Planning
Work Item | Work Class | Baseline (PM) | AI Difficulty | Essential | a_low | a_mode | a_high
Requirements gathering & analysis | Requirements | 1 |  | Yes
Agile ceremonies (planning, standup, retro, refinement) | Agile ceremonies | 0.8 |  | Yes
UX/UI design & wireframes | UX design | 0.8 |  | No
Solution architecture & technical design | Architecture | 1 |  | Yes
Data modeling & schema design | Data modeling | 0.6 |  | Yes
Compliance / security sign-off | Compliance | 0.4 |  | Yes

## Cloud & Infrastructure
Work Item | Work Class | Baseline (PM) | AI Difficulty | Essential | a_low | a_mode | a_high
Cloud infrastructure (IaC / Terraform, provisioning) | Cloud infra | 1 |  | No
Networking & cloud security (VPC, IAM) | Cloud infra | 0.6 |  | No
CI/CD pipeline setup | Deployment | 0.6 |  | No
Observability (logging, metrics, alerting) | Observability | 0.5 |  | No

## Backend & Data
Work Item | Work Class | Baseline (PM) | AI Difficulty | Essential | a_low | a_mode | a_high
REST/GraphQL API endpoints | REST API | 1.2 |  | No
Database schema & data access layer | Database | 0.8 |  | No
Integration with external/legacy systems | Integration | 1 |  | No
Authentication & authorization (security) | Security | 0.8 |  | No
Data migration / ETL | Data migration | 0.6 |  | No

## Frontend
Work Item | Work Class | Baseline (PM) | AI Difficulty | Essential | a_low | a_mode | a_high
Complex UI pages (business logic) | React UI | 1.5 |  | No
Simple / static pages | Simple page | 0.5 |  | No

## Quality & Testing
Work Item | Work Class | Baseline (PM) | AI Difficulty | Essential | a_low | a_mode | a_high
Test planning & strategy | Test planning | 0.4 |  | No
Automated tests (unit/integration/e2e) | Test automation | 1 |  | No
Manual & exploratory testing | Manual testing | 0.8 |  | No
Performance & load testing | Performance testing | 0.5 |  | No
User acceptance testing (UAT) | Manual testing | 0.5 |  | No
Code review & rework | Review | 0.6 |  | No

## Release & Ops
Work Item | Work Class | Baseline (PM) | AI Difficulty | Essential | a_low | a_mode | a_high
Deployment & release management | Deployment | 0.6 |  | No
Documentation (user & technical) | Documentation | 0.5 |  | No
Production support & maintenance | Support | 0.5 |  | No

## Config
Key | Value
Project | My Project
Team Size | 2
Unit | person-months
Claim Months